## due_dates_2019apr
paper | code | due_date | progress | journal | lead
IRB Data confidentiality | p103 | 2019-04-28 | submitted | CANREC | IRH
LAC Cohort description | p109 | 2019-04-30 | submitted | IJE | IRH
Trends in cardio-metabolic risk | p109 | 2019-04-30 | submitted | BMJ open | IRH
Rural and urban BMI trends | p109 | 2019-04-30 | accepted | Nature | IRH
SR pain in SCD | p123 | 2019-05-03 | submitted | Cochrane Library | IRH
SCD newborn screening | p123 | 2019-05-10 | submitted | J Med Screen | IRH
Seniors Driving Cessation | p115 | 2019-05-17 | drafted |  | CB
RPAQ validation | p124 | 2019-05-24 | drafted |  | CH
Caribbean prem. mortality | p122 | 2019-05-24 | planned |  | IRH
SCD growth | p123 | 2019-05-24 | not started |  | CH
5-year stroke survival | p116 | 2019-05-31 | not started |  | SA
HotN inactivity | p124 | 2019-05-31 | analysed |  | CH
Participatory Informatics | p101 | 2019-05-31 | submitted | Ethnicity and Disease | IRH
SCD pregnancy | p130 | 2019-05-31 | analysed |  | CH
5-year cancer survival | p117 | 2019-06-30 | not started |  | SA
Population aging | p102 | 2019-06-30 | not started |  | IRH
HotN diabetic foot | p124 | 2019-06-30 | drafted |  | CH
HotN Metabolic RF clusters | p124 | 2019-07-31 | drafted |  | CH
Lupus in St.Lucia | p113 | 2019-07-31 | analysed |  | CB
Availability of metrics | p104 | 2019-08-29 | not started |  | IRH
CFaH Food initiative barriers | p100 | 2019-08-31 | analysed |  | CB
HotN Diabetes access to care | p124 | 2019-09-30 | not started |  | NS
STEPS metrics in SIDS | p133 | 2019-09-30 | not started |  | SW
CVD risk score and CVD burden | p120 | 2019-09-30 | not started |  | CH
HotN Cost paper | p124 | 2019-10-31 | analysed |  | IRH
Composite SEP for ECHORN | p120 | 2019-10-31 | not started |  | CH
Does data affect decision | p129 | 2019-11-28 | not started |  | IRH
Inequalities in CVD burden | p120 | 2019-11-30 | not started |  | CH
CFaH Main paper | p100 | 2019-12-31 | analysed |  | IRH
Data sharing need assessment | p138 | 2019-12-31 | not started |  | IRH
CFaH environmental impacts | p100 | 2019-12-31 | not started |  | CB
CFaH perceptions of local food | p100 | 2019-12-31 | not started |  | CB
SSB paper 2 | p105 | 2019-12-31 | not started |  | IRH
Barriers to data sharing | p133 | 2020-01-31 | not started |  | IRH
Social dets of CVD burden | p120 | 2020-01-31 | not started |  | CH
Social dets of healthcare access | p120 | 2020-02-29 | not started |  | CH
CVD distribution in Caribbean | p120 | 2020-03-31 | not started |  | CH
CVD gender inequal in Caribbean | p120 | 2020-04-30 | not started |  | CH
Caribbean research links | p134 | 2020-06-30 | not started |  | IRH
SR social networks | p111 | 2020-06-30 | not started |  | CB

## due_dates_2019jun
paper | code | due_date | progress | journal | lead
IRB Data confidentiality | p103 | 2019-01-01 | submitted | CANREC | IRH
LAC Cohort description | p109 | 2019-01-15 | submitted | IJE | IRH
Trends in cardio-metabolic risk | p109 | 2019-01-31 | submitted | BMJ open | IRH
Rural and urban BMI trends | p109 | 2019-02-10 | accepted | Nature | IRH | 21915
SR pain in SCD | p123 | 2019-02-25 | submitted | Cochrane Library | IRH | 21946
SCD newborn screening | p123 | 2019-03-07 | submitted | J Med Screen | IRH | 21974
Participatory Informatics | p101 | 2019-03-16 | submitted | Ethnicity and Disease | IRH | 22005
SCD pregnancy | p130 | 2019-03-31 | drafted |  | CH | 22035
SCD growth | p123 | 2019-04-30 | not started |  | CH | 22066
HotN inactivity | p124 | 2019-05-15 | analysed |  | CH | 22096
Seniors Driving Cessation | p115 | 2019-05-22 | drafted | Ageing and Society | CB | 22127
RPAQ validation | p124 | 2019-05-31 | drafted |  | CH | 22158
5-year stroke survival | p116 | 2019-06-07 | not started |  | SA | 22188
HotN diabetic foot | p124 | 2019-06-16 | drafted |  | CH | 22219
5-year cancer survival | p117 | 2019-06-30 | not started |  | SA | 22250
Caribbean prem. mortality | p122 | 2019-07-08 | planned |  | IRH
HotN Metabolic RF clusters | p124 | 2019-07-16 | drafted |  | CH
Lupus in St.Lucia | p113 | 2019-07-23 | analysed |  | CB
Population aging | p102 | 2019-07-31 | not started |  | IRH
Availability of metrics | p104 | 2019-08-10 | not started |  | IRH
CFaH Food initiative barriers | p100 | 2019-08-20 | analysed |  | CB
HotN Diabetes access to care | p124 | 2019-09-10 | not started |  | NS
STEPS metrics in SIDS | p133 | 2019-09-20 | not started |  | SW
CVD risk score and CVD burden | p120 | 2019-09-30 | not started |  | CH
HotN Cost paper | p124 | 2019-10-21 | analysed |  | IRH
Composite SEP for ECHORN | p120 | 2019-10-31 | not started |  | CH
Does data affect decision | p129 | 2019-11-10 | not started |  | IRH
Inequalities in CVD burden | p120 | 2019-11-20 | not started |  | CH
CFaH Main paper | p100 | 2019-11-30 | analysed |  | IRH
CFaH environmental impacts | p100 | 2019-12-07 | not started |  | CB
Data sharing need assessment | p138 | 2019-12-14 | not started |  | IRH
CFaH perceptions of local food | p100 | 2019-12-22 | not started |  | CB
SSB paper 2 | p105 | 2019-12-31 | not started |  | IRH
Barriers to data sharing | p133 | 2020-01-21 | not started |  | IRH
Social dets of CVD burden | p120 | 2020-01-31 | not started |  | CH
Social dets of healthcare access | p120 | 2020-02-29 | not started |  | CH
CVD distribution in Caribbean | p120 | 2020-03-31 | not started |  | CH
CVD gender inequal in Caribbean | p120 | 2020-04-30 | not started |  | CH
Caribbean research links | p134 | 2020-05-30 | not started |  | IRH
SR social networks | p111 | 2020-06-30 | not started |  | CB

## Sheet2
PROPORTIONS
| Total number of papers | 40
| Not started | 22 | 55
| Analysed | 6 | 15 | 15
| Drafted | 4 | 10 | 25
| Submitted | 6 | 15 | 40
| Accepted | 1 | 2.5 | 42.5